Timeline and Tasks List for a Community-Based Research Proposal

This chart is developed from the Faculty Vitae Leadership Lesson, Grant-Writing Tools. It is designed to support planning for grant submissions, especially for community-based research grants. Users should develop their own dates and timelines to accommodate their particular grant submission needs.

| TASK |  | Days from Grant Submission |
| --- | --- | --- |
| ## Design Phase I of the Project—Capacity Building |  | Target – 30 days |
|  | - Define the problem | Target Date for Project__________ Phase I Deadline_________ Completion Date____________ |
|  | - Discuss current resources available to the community |  |
|  | - Define the collaborative |  |
|  | - Discuss procedures to ensure the Collaborative works |  |
| # Design Phase II of the Project—Research Study |  | Target – 30 days |
|  | # Review literature on the topic |  |
|  | # Write a brief literature review |  |
|  | # Discuss the rational for the study |  |
|  | # Develop study’s problem statement |  |
|  | # Develop study’s conceptual framework |  |
|  | # Develop study’s research questions |  |
|  | Develop study’s methodology: Mixed-method qualitative and quantitative |  |
|  | Discuss data collection strategies: Focus groups and survey |  |
|  | Design sampling strategy for the qualitative and quantitative components |  |
|  | Discuss methods for ensuring validity and reliability (triangulation, feedback from study participants) |  |
|  | Develop analysis plan for qualitative and quantitative data |  |

| Complete Other Sections of the Proposal |  | Target – 22 days |
| --- | --- | --- |
|  | ## Complete the proposal application forms |  |
|  | ## Complete the proposal narrative (project objectives, deliverables and outcomes, communications strategy, staffing, timeline, ect.) |  |
|  | ## Complete the budget and budget narrative |  |
|  | ## Collect additional pieces of information (faculty vitas and resumes, legal and final documents, etc.) |  |
| # Review and Submission Process |  | ## Target- 20 days |
|  | 1st Draft of entire proposal to readers |  |
|  | Review comments |  |
| # Final Revision |  | Target – 10 days |
|  | # Submit Proposal | Target date |
| According to the grant announcement, the review process might take: |  |  |