## Slide 1: Community Health Workers using Patient Stories
Lee Hargraves (Family Medicine and Community Health)
Barry Saver (Family Medicine and Community Health)
Warren Ferguson (Family Medicine and Community Health)
Daniel Mullin (Family Medicine and Community Health)
Debra Bonollo (Family Medicine and Community Health)
Sharina Person (Quantitative Health Sciences)

## Slide 2: Specific Aims
AIM 1: Create Storytelling DVDs in two Community Health Centers
AIM 2: Enhance and Expand Community Health Worker (CHW) Curriculum and Training
AIM 3: Recruit Participants and Conduct CHW-Storytelling Intervention

## Slide 3: Progress Toward Aim 1: Create Storytelling DVDs in English and Spanish
CHWs contact patients using a script developed by the team (either in person or on the phone) to identify patients who have made changes in hypertension control
Two group interviews of 8-10 potential stars at each site are scheduled in the next two weeks
4-6 individual videotaped interviews with video potential stars will occur at each site

## Slide 4
Core concepts for the intervention have been identified for integration into the training of CHWs and the development of storytelling videos.
A training for CHWs to use motivational interviewing (5 sessions of 4 hours in duration) with patients has been scheduled for January – March 2013.
A CHW manual with additional materials (e.g., encounter forms, references for healthy heart cooking, community resources) is in development.
Progress Toward Aim 2: Enhance and Expand CHW Curriculum and Training

## Slide 5: Challenges/Questions
Patients are cared for in community health centers that serve culturally and linguistically diverse communities.
In Spanish, patients will come from many places, e.g., Dominican Republic, Puerto Rican, El Salvador
In English, much more diversity exists.
How do we include potential stars who are patients of the health centers, but come from communities less represented?
  For example, one center has patients from Ghana and Liberia
  The other center has a population of people from Cambodia